## Slide 1
21st Century School Buildings Plan
SCHOOL Patterson High School & Claremont Middle/High Elementary School
COMMUNITY MEETING Construction Update| October 8, 2019

## Slide 2
Introductions and Agenda
Design
Exterior Views and Landscape
Schedule
Site Phasing Plan
“What’s happening now”
Next Steps
Feedback
Alicia Thomas
21st Century School Buildings Program
Program Coordinator
Baltimore City Schools
Tiara Moorman
Project Manager
Maryland Stadium Authority
Jerry Marinzel
Project Architect
Stantec
Aaron Mengel
Senior Project Manager
Skanska Construction Company
Introductions
Agenda
Notes: Abut USA Architects: About us……
30 Year Old Regional Architectural Firm
Extensive K-12 School Design Portfolio
Extensive Experience in Public Projects
Completion of Multiple LEED Projects
USA CEO Led Concept Design for the Frederick Addition

## Slide 3
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org
Design
Design

## Slide 4
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 5
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 6
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 7
Demolition & Construction Phases
Project Schedule
Phase 1 & 2 – Construction of new Patterson High School & Claremont Middle/High School
                Duration 24 months starting at Notice to Proceed (NTP)
                July 2019 to June 2021
Phase 3 – Abatement and Demolition of the Existing Patterson High School & Site Construction
July 2021 to June 2022
Basic overview
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 8
Demolition & Construction Phases
Hours of Operation
                6 am to 7 pm
Truck Plan
MD 95
Eastern Avenue
Kane St
No idling or overnight deliveries
Rodent Plan
Rodent mitigation for both construction and demo phases
Logistics
Waste management will be handled by onsite dumpsters
Regular street sweeping to keep roads clean
Site security will be provided by perimeter fence and cameras
Basic overview
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 9: Phase 1 & 2 Logistics
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 10: Phase 3a Logistics
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 11: Phase 3 Logistics
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 12: Area A Foundations
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 13: Site Work & Utilities
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 14: Area C, D and E Rammed Aggregate Piers
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 15
Next Steps
Excavate and install building footings
Install MEP under-slab rough-ins
Install building footings
Install under slab vapor barrier
Install building CMU walls in Area A
Install steel framing in Area A
Install slab on grade Area A
All work proceeds Area A>B>C>D>E
Site utility installation
Retaining walls along tennis courts
Community Meeting: “Construction Update” | Patterson High School & Claremont Middle/High School | October 8, 2019 | www.baltimore21stcenturyschools.org

## Slide 16
CONTACTS
Alicia Thomas
AThomas03@bcps.k12.md.us
21st Century School Buildings
Program Office
(443) 642-4600
www.baltimore21stcenturyschools.org
Instagram
@21stCSBaltimore
Twitter
@21stCSBaltimore
Facebook
@21stCenturySchoolBuildingsProgram
Questions?

## Slide 17
21st Century School Buildings Program Baltimore City Public Schools 200 East North Avenue Room 407-B
Baltimore MD 21202
(443) 642-4600
Dorothy Hellman Executive Director, 21st Century Buildings Program Baltimore City Public Schools
Gary McGuigan Senior Vice President, Capital Development Division Maryland Stadium Authority
James T. Smith, Jr. Chief of Strategic Alliances City of Baltimore
Robert Gorrell Executive Director, Public School Construction Program State of Maryland
www.baltimore21stcenturyschools.org
This presentation is brought to you by the
21st Century School Buildings Program.
Thank You!